# Agile Plan — Kids Clinic Management System

Scrum Methodology · IEEE 830-1998 Compliant · v2.0

## Table of Contents

- Scrum Framework

  - 1.1 Why Agile / Scrum

  - 1.2 Scrum Roles

  - 1.3 Scrum Ceremonies

- User Stories & Acceptance Criteria

  - Sprint 1 — Foundation: Authentication & Core Setup

  - Sprint 2 — Patient Management Core

  - Sprint 3 — Visit Scheduling

  - Sprint 4 — Consultation Management

  - Sprint 5 — Prescription Management

  - Sprint 6 — Vaccination Management

  - Sprint 7 — Financial Management & Reporting

  - Sprint 8 — Polish & System Hardening

- Product Backlog

- Sprint Planning

  - 4.1 Sprint 1 — Foundation

  - 4.2 Sprint 2 — Patient Management

  - 4.3 Sprint 3 — Visit Scheduling

  - 4.4 Sprint 4 — Consultation Management

  - 4.5 Sprint 5 — Prescription Management

  - 4.6 Sprint 6 — Vaccination Management

  - 4.7 Sprint 7 — Financial Management

  - 4.8 Sprint 8 — System Hardening

  - 4.9 Project Velocity Summary

- Definition of Done

## 1. Scrum Framework

The original Waterfall methodology has been replaced with Agile Scrum to enable iterative development, continuous stakeholder feedback, and adaptive planning.

### 1.1 Why Agile / Scrum

| Aspect | Scrum Implementation |
| --- | --- |
| Iterations | 2-week Sprints delivering potentially shippable increments |
| Requirements | Living Product Backlog refined through ongoing stakeholder collaboration |
| Testing | Continuous integration testing within each Sprint |
| Delivery | Incremental feature releases enabling early value realization |
| Flexibility | Sprint Retrospectives drive process improvement and adaptation |
| Stakeholder Engagement | Sprint Reviews provide regular demo and feedback opportunities |

### 1.2 Scrum Roles

| Role | Who | Responsibilities |
| --- | --- | --- |
| Product Owner | The Doctor | Defines priorities, accepts/rejects deliverables, manages Product Backlog |
| Scrum Master | Project Team Lead | Facilitates ceremonies, removes impediments, coaches the team |
| Development Team | Full-stack developers + QA | Self-organizing, cross-functional, delivers working increments |

### 1.3 Scrum Ceremonies

| Ceremony | Duration | Purpose |
| --- | --- | --- |
| Sprint Planning | 4 hours | Select and commit to Sprint Backlog items from Product Backlog |
| Daily Stand-up | 15 min | Synchronize activities, identify blockers, adjust plan |
| Sprint Review | 2 hours | Demo increment to stakeholders, gather feedback |
| Sprint Retrospective | 1.5 hours | Inspect and adapt processes for next Sprint |
| Backlog Refinement | 2 hours/week | Estimate, prioritize, and clarify upcoming items |

## 2. User Stories & Acceptance Criteria

Each story follows the Connextra format: "As a [role], I want [feature], so that [benefit]." Acceptance Criteria use Given-When-Then format. Story Points follow the Fibonacci scale: 1 · 2 · 3 · 5 · 8.

### 🏁 Sprint 1 — Foundation: Authentication & Core Setup

#### US-001 · Login to the System

3 SP · High · REQ-001

As a Doctor or Employee, I want to log in with my username and password, so that I can securely access the system.

| # | Acceptance Criterion |
| --- | --- |
| AC1.1 | Given the user is on the login page, When they enter valid credentials and click Login, Then they are redirected to the dashboard within 3 seconds. |
| AC1.2 | Given the user enters invalid credentials, When they click Login, Then an error message "Invalid username or password" is displayed without revealing which field is incorrect. |
| AC1.3 | Given the user is authenticated, When 30 minutes of inactivity passes, Then the session expires and the user is redirected to the login page. |

#### US-002 · Manage User Accounts

5 SP · High · REQ-032

As a Doctor, I want to create and manage user accounts, so that I can control system access for clinic staff.

| # | Acceptance Criterion |
| --- | --- |
| AC2.1 | Given the Doctor is logged in, When they navigate to User Management and fill in username, password, and role, Then a new user is created and can immediately log in. |
| AC2.2 | Given the Doctor views the user list, When they click Edit on a user, Then they can modify the user's role and save changes. |
| AC2.3 | Given the Doctor attempts to delete a user, When the user has associated records, Then deletion is prevented with a message explaining the dependency. |

### 👶 Sprint 2 — Patient Management Core

#### US-003 · Add a New Child's Profile

5 SP · High · REQ-006

As a Doctor or Employee, I want to add a new child's medical profile, so that the clinic has complete patient records.

| # | Acceptance Criterion |
| --- | --- |
| AC3.1 | Given the user is logged in, When they navigate to Add Child and enter required fields (name, DOB, gender, parent name, phone), Then the record is saved and a success message is displayed. |
| AC3.2 | Given required fields are missing, When the user submits the form, Then validation errors appear next to each missing field. |
| AC3.3 | Given a child with the same name and DOB exists, When the user attempts to add, Then a duplicate warning is shown with a link to the existing record. |

#### US-004 · View List of Registered Children

3 SP · High · REQ-005

As a Doctor or Employee, I want to view a list of all registered children, so that I can quickly find patient records.

| # | Acceptance Criterion |
| --- | --- |
| AC4.1 | Given the user is logged in, When they click "Children's List", Then a paginated table shows all children sorted by registration date (newest first). |
| AC4.2 | Given the list has more than 20 records, When displayed, Then pagination controls are available. |
| AC4.3 | Given the list is empty, When displayed, Then an informational message appears with a link to add the first child. |

#### US-005 · Search for Children by Name

2 SP · High · REQ-009

As a Doctor or Employee, I want to search for children by name, so that I can quickly locate a specific patient.

| # | Acceptance Criterion |
| --- | --- |
| AC5.1 | Given the user is on the Children's List page, When they type 3+ characters in the search box, Then results filter in real-time showing matching names. |
| AC5.2 | Given no results match the search term, When the user searches, Then a "No results found" message is displayed with an option to clear the search. |

#### US-006 · Edit or Delete a Child's Record

3 SP · High · REQ-007, REQ-008

As a Doctor or Employee, I want to edit or delete a child's record, so that I can correct errors or remove obsolete entries.

| # | Acceptance Criterion |
| --- | --- |
| AC6.1 | Given the user selects a child record, When they click Edit, Then a pre-filled form appears allowing modification of all fields. |
| AC6.2 | Given the user clicks Delete, When a confirmation dialog appears and they confirm, Then the record is soft-deleted (hidden but recoverable). |
| AC6.3 | Given the child has linked prescriptions, When the user attempts deletion, Then deletion is blocked with a message listing the dependencies. |

### 📅 Sprint 3 — Visit Scheduling

#### US-007 · Schedule a Medical Visit

5 SP · High · REQ-010

As a Doctor or Employee, I want to schedule a medical visit for a child, so that appointments are properly organized.

| # | Acceptance Criterion |
| --- | --- |
| AC7.1 | Given a child record exists, When the user clicks "Schedule Visit" and enters date, time, type, and notes, Then the visit is saved and appears in the child's history. |
| AC7.2 | Given the selected time slot conflicts with an existing visit, When the user submits, Then a conflict warning is displayed with overlapping visit details. |
| AC7.3 | Given the visit date is in the past, When the user submits, Then a validation error prevents scheduling with a clear message. |

#### US-008 · View Today's Scheduled Visits

3 SP · High · REQ-011

As a Doctor or Employee, I want to view today's scheduled visits, so that I can prepare for the day's appointments.

| # | Acceptance Criterion |
| --- | --- |
| AC8.1 | Given the user is logged in, When they open the dashboard or "Today's Visits", Then all visits for the current date are displayed sorted by time. |
| AC8.2 | Given there are no visits today, When the page loads, Then an empty state message appears with a button to schedule a visit. |

#### US-009 · Edit or Cancel a Scheduled Visit

5 SP · High · REQ-013, REQ-014

As a Doctor or Employee, I want to edit or cancel a scheduled visit, so that I can accommodate changes in the schedule.

| # | Acceptance Criterion |
| --- | --- |
| AC9.1 | Given a visit exists, When the user clicks Edit, Then all visit details are editable and changes are saved with an audit trail. |
| AC9.2 | Given a visit exists, When the user clicks Cancel/Delete and confirms, Then the visit is removed from the schedule and the child's history notes the cancellation. |

#### US-010 · View a Child's Complete Visit History

3 SP · Medium · REQ-012

As a Doctor or Employee, I want to view a child's complete visit history, so that I can review past medical encounters.

| # | Acceptance Criterion |
| --- | --- |
| AC10.1 | Given a child record is selected, When the user clicks "Visit History", Then all past visits are displayed in reverse chronological order. |
| AC10.2 | Given the history is long, When displayed, Then results are paginated with filters for date range and visit type. |

### 🩺 Sprint 4 — Consultation Management

#### US-011 · Schedule a Consultation Linked to a Visit

5 SP · High · REQ-015

As a Doctor or Employee, I want to schedule a consultation linked to a visit, so that medical encounters are properly documented.

| # | Acceptance Criterion |
| --- | --- |
| AC11.1 | Given a visit is selected, When the user clicks "Add Consultation" and enters symptoms, diagnosis, notes, and doctor, Then the consultation is saved and linked to the visit. |
| AC11.2 | Given a consultation is added, When the visit list is viewed, Then a visual indicator shows that the visit has an associated consultation. |

#### US-012 · View Consultation History

3 SP · Medium · REQ-016

As a Doctor or Employee, I want to view consultation history, so that I can review past diagnoses and treatments.

| # | Acceptance Criterion |
| --- | --- |
| AC12.1 | Given a child or visit is selected, When the user clicks "Consultation History", Then all consultations are displayed with doctor, date, diagnosis, and symptoms. |
| AC12.2 | Given consultations exist, When viewing history, Then each entry is expandable to show full details including attached prescriptions. |

### 💊 Sprint 5 — Prescription Management (Doctor Only)

#### US-013 · Create a Prescription

5 SP · High · REQ-017, REQ-022

As a Doctor, I want to create a prescription for a consultation, so that medications are properly documented and printable.

| # | Acceptance Criterion |
| --- | --- |
| AC13.1 | Given a consultation is selected, When the Doctor clicks "Add Prescription" and enters medication, dosage, frequency, duration, and instructions, Then the prescription is saved and linked to the consultation. |
| AC13.2 | Given an Employee attempts to add a prescription, When they access the prescription form, Then access is denied with a role-appropriate message. |
| AC13.3 | Given required prescription fields are missing, When the Doctor submits, Then validation errors appear for each missing field. |

#### US-014 · Edit or Delete a Prescription

3 SP · Medium · REQ-018, REQ-019

As a Doctor, I want to edit or delete a prescription, so that I can correct errors or cancel prescriptions.

| # | Acceptance Criterion |
| --- | --- |
| AC14.1 | Given a prescription exists and is not dispensed, When the Doctor clicks Edit, Then the prescription is editable and changes are saved. |
| AC14.2 | Given a prescription exists, When the Doctor clicks Delete and confirms, Then the prescription is removed with an audit log entry. |

#### US-015 · Print a Prescription

3 SP · High · REQ-020

As a Doctor, I want to print a prescription, so that I can provide a physical copy to the patient's guardian.

| # | Acceptance Criterion |
| --- | --- |
| AC15.1 | Given a prescription exists, When the Doctor clicks Print, Then a print-ready page opens with clinic letterhead, patient details, and prescription formatted for standard A4 paper. |
| AC15.2 | Given the print dialog, When the Doctor confirms, Then the prescription prints correctly with all fields legible. |

#### US-016 · View All Prescription Records

3 SP · Medium · REQ-021

As a Doctor, I want to view all prescription records, so that I can track medication history for any patient.

| # | Acceptance Criterion |
| --- | --- |
| AC16.1 | Given the Doctor navigates to Prescriptions, When the page loads, Then a filterable list shows all prescriptions with patient name, medication, date, and doctor. |
| AC16.2 | Given the Doctor filters by patient name, When applied, Then only prescriptions for that patient are shown. |

### 💉 Sprint 6 — Vaccination Management

#### US-017 · Manage the Vaccine Catalog

5 SP · High · REQ-028

As a Doctor or Employee, I want to manage the vaccine catalog, so that the system maintains an accurate list of available vaccines.

| # | Acceptance Criterion |
| --- | --- |
| AC17.1 | Given the user is logged in, When they navigate to Vaccine Catalog and add a new vaccine with name, type, and manufacturer, Then the vaccine appears in the catalog. |
| AC17.2 | Given a vaccine is linked to historical records, When the user attempts to delete it, Then deletion is prevented with a message explaining the dependency. |

#### US-018 · Record a Vaccination for a Child

5 SP · High · REQ-023

As a Doctor or Employee, I want to record a vaccination for a child, so that immunization history is properly tracked.

| # | Acceptance Criterion |
| --- | --- |
| AC18.1 | Given a child record exists, When the user selects a vaccine from the catalog, enters batch number, date, and next due date, Then the vaccination record is saved. |
| AC18.2 | Given a vaccination is recorded with a next due date, When that date approaches, Then the child appears in upcoming vaccination reminders. |

#### US-019 · View a Child's Vaccination History

3 SP · High · REQ-024

As a Doctor or Employee, I want to view vaccination history, so that I can verify immunization completeness.

| # | Acceptance Criterion |
| --- | --- |
| AC19.1 | Given a child record is selected, When the user clicks "Vaccination History", Then all vaccinations are displayed in chronological order with vaccine name, date, and next due date. |
| AC19.2 | Given vaccinations exist, When viewing history, Then overdue vaccinations are highlighted in red for immediate attention. |

#### US-020 · View Today's Vaccination Records

3 SP · Medium · REQ-025, REQ-026

As a Doctor or Employee, I want to view today's vaccination records, so that I can prepare and verify daily immunization activities.

| # | Acceptance Criterion |
| --- | --- |
| AC20.1 | Given the current date, When the user opens "Today's Vaccinations", Then all vaccinations scheduled or administered today are displayed. |
| AC20.2 | Given a vaccination record is displayed, When the user clicks Edit, Then the record becomes editable with validation. |

### 💰 Sprint 7 — Financial Management & Reporting

#### US-021 · View Daily Account Summary

3 SP · Medium · REQ-029

As a Doctor, I want to view daily account summaries, so that I can track daily revenue and visit volume.

| # | Acceptance Criterion |
| --- | --- |
| AC21.1 | Given the Doctor navigates to Daily Accounts, When the page loads, Then a summary shows the selected date, total visits, and total revenue. |
| AC21.2 | Given no visits occurred on the selected date, When the summary is viewed, Then zero values are displayed with an informational message. |

#### US-022 · View Monthly Account Summary

3 SP · Medium · REQ-030

As a Doctor, I want to view monthly account summaries, so that I can analyze monthly performance trends.

| # | Acceptance Criterion |
| --- | --- |
| AC22.1 | Given the Doctor selects a month and year, When they view the summary, Then total visits, total revenue, and average revenue per visit are displayed. |
| AC22.2 | Given the summary is viewed, When data exists, Then a comparison with the previous month is shown as a percentage change. |

#### US-023 · Restrict Financial Access to Doctor Only

3 SP · High · REQ-031

As a Doctor, I want financial summaries to be accessible only to me, so that financial data remains confidential.

| # | Acceptance Criterion |
| --- | --- |
| AC23.1 | Given an Employee attempts to access the Accounts section, When they navigate to it, Then access is denied and they are redirected to the dashboard. |
| AC23.2 | Given the Doctor accesses financial data, When viewing, Then all monetary values are formatted to 2 decimal places with currency symbol. |

### 🔧 Sprint 8 — Polish & System Hardening

#### US-024 · Graceful Error Handling

3 SP · Medium · NFR-013

As a user, I want the system to handle errors gracefully, so that I can recover from unexpected issues.

| # | Acceptance Criterion |
| --- | --- |
| AC24.1 | Given any system error occurs, When detected, Then a user-friendly error page is shown with options to retry or return home. |
| AC24.2 | Given a database connection fails, When the user performs an action, Then the error is logged and a maintenance message is displayed. |

#### US-025 · Audit Logging for All Data Operations

5 SP · Medium · NFR-008

As a user, I want all data operations to be logged, so that the clinic maintains an audit trail.

| # | Acceptance Criterion |
| --- | --- |
| AC25.1 | Given any create, update, or delete operation, When performed, Then an audit log entry records the user, timestamp, action type, and affected record. |
| AC25.2 | Given the audit log, When viewed by a Doctor, Then entries are filterable by date range, user, and action type. |

## 3. Product Backlog

Total: 92 Story Points across 25 stories · Ordered by business value and dependency.

| Rank | ID | User Story | SP | Priority | Sprint |
| --- | --- | --- | --- | --- | --- |
| 1 | US-001 | Login to system | 3 | High | S1 |
| 2 | US-002 | Manage user accounts | 5 | High | S1 |
| 3 | US-004 | View children's list | 3 | High | S2 |
| 4 | US-003 | Add child record | 5 | High | S2 |
| 5 | US-005 | Search children by name | 2 | High | S2 |
| 6 | US-006 | Edit / delete child record | 3 | High | S2 |
| 7 | US-007 | Schedule medical visit | 5 | High | S3 |
| 8 | US-008 | View today's visits | 3 | High | S3 |
| 9 | US-009 | Edit / cancel visit | 5 | High | S3 |
| 10 | US-010 | View visit history | 3 | Medium | S3 |
| 11 | US-011 | Schedule consultation | 5 | High | S4 |
| 12 | US-012 | View consultation history | 3 | Medium | S4 |
| 13 | US-013 | Create prescription | 5 | High | S5 |
| 14 | US-014 | Edit / delete prescription | 3 | Medium | S5 |
| 15 | US-015 | Print prescription | 3 | High | S5 |
| 16 | US-016 | View prescription log | 3 | Medium | S5 |
| 17 | US-017 | Manage vaccine catalog | 5 | High | S6 |
| 18 | US-018 | Record vaccination | 5 | High | S6 |
| 19 | US-019 | View vaccination history | 3 | High | S6 |
| 20 | US-020 | View today's vaccinations | 3 | Medium | S6 |
| 21 | US-021 | Daily account summary | 3 | Medium | S7 |
| 22 | US-022 | Monthly account summary | 3 | Medium | S7 |
| 23 | US-023 | Financial access control | 3 | High | S7 |
| 24 | US-024 | Error handling & recovery | 3 | Medium | S8 |
| 25 | US-025 | Audit logging system | 5 | Medium | S8 |

## 4. Sprint Planning

Sprint Length: 2 weeks | Team Size: 3 developers (Full-stack + QA) | Fibonacci Scale: 1 · 2 · 3 · 5 · 8

### 4.1 Sprint 1 — Foundation

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Establish secure access control and user administration capabilities |
| Duration | 2 weeks |
| Team Capacity | 12 Story Points |
| Stories | US-001 (3 SP) · US-002 (5 SP) |
| Total Committed | 8 SP |
| Deliverables | Working login system · User management interface · RBAC · Session management |

### 4.2 Sprint 2 — Patient Management

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Enable complete CRUD operations for patient records with search capability |
| Duration | 2 weeks |
| Team Capacity | 10 Story Points |
| Stories | US-003 (5 SP) · US-004 (3 SP) · US-005 (2 SP) |
| Total Committed | 10 SP |
| Deliverables | Child registration form · Paginated list with search · Edit/delete with validation · Duplicate detection |

### 4.3 Sprint 3 — Visit Scheduling

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Implement complete visit scheduling with conflict detection and daily views |
| Duration | 2 weeks |
| Team Capacity | 10 Story Points |
| Stories | US-007 (5 SP) · US-009 (5 SP) |
| Total Committed | 10 SP |
| Deliverables | Visit scheduling with time conflict detection · Today's visit dashboard · Visit history with filters |

### 4.4 Sprint 4 — Consultation Management

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Link consultations to visits with full history tracking |
| Duration | 2 weeks |
| Team Capacity | 14 Story Points |
| Stories | US-011 (5 SP) · US-012 (3 SP) · US-006 (3 SP) · US-010 (3 SP) |
| Total Committed | 14 SP |
| Deliverables | Consultation form linked to visits · Expandable history view · Diagnosis recording |

### 4.5 Sprint 5 — Prescription Management

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Enable complete prescription lifecycle with printing capability |
| Duration | 2 weeks |
| Team Capacity | 14 Story Points |
| Stories | US-013 (5 SP) · US-014 (3 SP) · US-015 (3 SP) · US-016 (3 SP) |
| Total Committed | 14 SP |
| Deliverables | Prescription CRUD with role enforcement · Print-ready A4 template · Filterable prescription log |

### 4.6 Sprint 6 — Vaccination Management

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Implement vaccination tracking with catalog management and overdue highlighting |
| Duration | 2 weeks |
| Team Capacity | 10 Story Points |
| Stories | US-017 (5 SP) · US-018 (5 SP) |
| Total Committed | 10 SP |
| Deliverables | Vaccine catalog CRUD · Vaccination recording with batch tracking · History with overdue alerts |

### 4.7 Sprint 7 — Financial Management

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Provide financial oversight with daily/monthly summaries and strict access control |
| Duration | 2 weeks |
| Team Capacity | 9 Story Points |
| Stories | US-021 (3 SP) · US-022 (3 SP) · US-023 (3 SP) |
| Total Committed | 9 SP |
| Deliverables | Daily/monthly financial summaries with comparison · Role-based access enforcement |

### 4.8 Sprint 8 — System Hardening

| Attribute | Detail |
| --- | --- |
| Sprint Goal | Ensure production readiness with error handling, audit logging, and final polish |
| Duration | 2 weeks |
| Team Capacity | 8 Story Points |
| Stories | US-024 (3 SP) · US-025 (5 SP) |
| Total Committed | 8 SP |
| Deliverables | Global error handling · Audit logging system · Final bug fixes · Deployment preparation |

### 4.9 Project Velocity Summary

| Metric | Planned | Notes |
| --- | --- | --- |
| Total Story Points | 92 SP | Corrected from v1.0 (was 71) |
| Sprint Count | 8 sprints | 2-week sprints |
| Average Velocity | 11.5 SP / sprint | Stable throughput |
| Project Duration | 16 weeks | ~4 months calendar time |
| Team Size | 3 developers | Full-stack + QA |

Sprint Timeline (16 weeks)

S1  S2  S3  S4  S5  S6  S7  S8
│   │   │   │   │   │   │   │
├───┤   │   │   │   │   │   │   Auth & Users         (8 SP)
    ├───┤   │   │   │   │   │   Patient Core         (10 SP)
        ├───┤   │   │   │   │   Visit Scheduling     (10 SP)
            ├───┤   │   │   │   Consultations        (14 SP)
                ├───┤   │   │   Prescriptions        (14 SP)
                    ├───┤   │   Vaccinations         (10 SP)
                        ├───┤   Financial Reports     (9 SP)
                            ├───┤ System Hardening    (8 SP)
                                                  ─────────
                                           Total:    92 SP

## 5. Definition of Done

A Product Backlog Item is DONE only when ALL of the following criteria are met.

| # | Criterion | Verified By |
| --- | --- | --- |
| 1 | Code is written and follows project coding standards | Code review |
| 2 | Unit tests written with minimum 80% code coverage | Coverage report |
| 3 | Integration tests pass for all affected modules | Integration test run |
| 4 | All Acceptance Criteria are met and verified | Test execution log |
| 5 | Code review completed with no critical issues | Review tool |
| 6 | Functional testing completed on target browsers (Chrome · Firefox · Edge) | Test report |
| 7 | Documentation updated (user guide, technical docs) | Doc review |
| 8 | No known critical or high-severity defects | Defect tracker |
| 9 | Performance criteria met (page load < 3 seconds) | Performance test |
| 10 | Feature demonstrated in Sprint Review and accepted by Product Owner | Sprint Review minutes |

Kids Clinic Management System · Agile Plan v2.0 · Computer Science Department · 2025